## Sheet1
| APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  | JULY |  |  |  | AUGUST |  |  |  | SEPTEMBER |  |  |  | OCTOBER
| WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4
Onboarding
Literature Review/Project Set Up
ALL | MAY WK 3: Data Collection, Data QA/QC & Progress Report
[7 empty] | Well Log/Facies Analysis | [15 empty] | Coach Review |  | Presentation
QI/PS | MAY WK 3: Formation Evaluation; JUNE WK 1: Environment of Deposition & Conceptual Model / Saturation Hieght Modelling
PS | MAY WK 4: Seismic to well tie; JULY WK 1: Structural Modelling & Fluid Distribution; JULY WK 4: Coach Review
QI | MAY WK 4: Coach Review; JUNE WK 1: Fault & Horizon Interpretation; JUNE WK 4: Velocity Modelling/ T-D Conversion/Structural Modelling; JULY WK 1: Q.I (Inversion: X-Plots); AUGUST WK 4: Coach Review
PP/PG | JUNE WK 3: Attribute Extraction & Analysis; JUNE WK 4: Coach Review; JULY WK 2: Facies & Property Modelling
RE | JULY WK 4: 3D Static Model; AUGUST WK 3: Volumetrics/Uncertainty Analysis
PT | MAY WK 3: Data Gathering, QA/QC, Data Analysis, Pressure, Production & PVT Data; MAY WK 4: Fluid Characterization/Evaluate Initial /Current Reservoir Conditions; JUNE WK 2: Relative Permeability Modelling; JUNE WK 4: Generate/include Fills for Model Visualization & Coach Review; JULY WK 1: Dynamic Modelling Initialisation; SEPTEMBER WK 2: Volumetrics/Economics
[12 empty] | Well Design Consideration | Well Modelling& Generation of Lift Curve |  |  |  |  | History Matching & Prediction